## Tracker
Track Installation
Segment | Planned Mi | Completed Mi (Previous) | Completed Mi (Current) | % Completion | Completed Mi % (Previous) | Completed Mi % (This Week) | Notes
Central Urban Corridor | 19 mi | 12 mi | 16 mi | 84% |  |  | Advanced machinery and night shifts increased pace. Monitor potential community noise concerns.
Southeastern Quadrant | 15 mi | 6 mi | 10 | 66.67% |  | 26.67% | Recent equipment upgrades significantly improved installation rate. Continued focus on maintaining momentum.
Eastern Section | 12 mi | 6 mi | 6 | 50% |  | 0% | No progress due to rocky terrain. Exploring alternative methods and potential rerouting. Strategic review needed.
Western Industrial Area | 22 mi | 9 mi | 16 mi | 73% |  |  | Accelerated progress with enhanced equipment deployment. Optimize resource allocation to sustain pace.
Electrification
Component | Planned Units | Completed Units (Previous) | Completed Units (Current) | % Completion | Completed Units % (Previous) | Completed Units % (This Week) | Notes
Track Electrification | 68 mi | 24 mi | 30 | 44.12% |  | 8.824% | Significant progress with 6 mi electrified recently. Continuing efforts to stay on track.
Substations Construction | 5 | 2 | 2 | 40% |  | 0% | No new substations completed. Delay in electrical components impacts schedule.

## Dashboard
Metroville Urban Rail Expansion — Project Dashboard
TRACK INSTALLED |  | ELECTRIFIED |  | BUDGET SPENT |  | COMMUNITY
32 / 68 mi |  | 30 / 68 mi |  | $90M → $125M est. |  | Engagement: Good
47% complete |  | 44% complete |  | ⚑ Over budget |  | ⚑ Noise complaints
TRACK INSTALLATION PROGRESS
Segment | Planned | Prev (mi) | Current (mi) | % Done | Δ This Week | Status | Notes
Central Urban Corridor | 19 mi | 12 mi | 16 mi | 84.21% | 21.05% | ✓ On track | Night shifts boosted pace. Watch noise concerns.
Southeastern Quadrant | 15 mi | 6 mi | 10 mi | 66.67% | 26.67% | ✓ Good pace | Equipment upgrade driving gains.
Eastern Section | 12 mi | 6 mi | 6 mi | 50% | 0% | ⚑ Stalled | Zero progress. Rocky terrain. Review underway.
Western Industrial Area | 22 mi | 9 mi | 16 mi | 72.73% | 31.82% | ✓ On track | Strong gains with upgraded equipment.
ELECTRIFICATION MILESTONES
Segment | Planned | Prev (mi) | Current (mi) | % Done | Δ This Week | Status | Notes
Track Electrification | 68 mi | 24 mi | 30 mi | 44.12% | 8.824% | ✓ Progressing | 6 new miles this period. Terrain adding cost pressure.
Substations Construction | 5 | 2 | 2 | 40% | 0% | ⚑ Delayed | No new substations. Electrical component delays ongoing.
BUDGET SUMMARY |  |  |  | COMMUNITY FEEDBACK
Budget spent to date |  | $90M |  | ✓ | Engagement praised | Residents appreciate transparency & open consultation.
Projected final cost |  | $125M |  | ✓ | Communication effective | Community feels informed and heard.
Variance vs estimate |  | ⚑ Over budget |  | ⚑ | Noise complaints rising | Nighttime construction in Eastern Section a concern.
Primary cost driver |  | Eastern Section terrain |  | ⚑ | Daytime hours requested | Residents want work limited to daytime. Action needed.

## ChartData
Segment | Planned (mi) | Completed (mi)
Central Urban Corridor | 19 | 16
Southeastern Quadrant | 15 | 10
Eastern Section | 12 | 6
Western Industrial Area | 22 | 16